## UNO
Card | Card Reader
Image | Camera
Finger | morpho | Core configuration
Document | scanner | Sentinal |  |  | Services
NA | printer | Perso |  |  | Email and SMS service | 1. Email will be send from pop3, gmail, hotmail. 2. Sms sending :- modem / web based sms api ( Please provide the same if we want to used).
ID card | ID card designer and printing | tempus |  |  | Communication service | Re wamp is done
Time sheet
Leaave rule
Sr. No | Modules | Feature / Module | Functionality
1 | Core configuration | 1. Company level sepration of all masters. 2. Common Entity i. Location ii. Division / Zone iii. Department iv. Designation v. Grade vi. Group viii. Category 3. Workflow level
|  | Reasone master | Modulewise ie Tempus, Perso | Vaibhav to add. | Add column Module From Module table
|  | 1. User Creation 2. password maintance / Reset 3. Login after password reset | 1. 2. User can change password if he / she knows previous password after loging to the protal. 3. A user can reset his own password, the OTP will be send via registred Email/ SMS. 4. On reset of password user has to change his default password. Without this he /she can not procced. 5. On password reset OTP will get stored in place of Password. |  | Add coloum ispasswordReset
|  | Holiday Master | 1. Yearly holiday will be added based on leave year defined also Location wise option will be present. 2. Holidays can be optional.
|  | Employee Master | 1. Personal details including Adhar, PAN, Family, PF/ UAN its Nomination, NPS Nomination, Nomination, Spouse, Father , Mother, Childrens 2. Official details 3. Address details 4. User 5. In case we have provided sentinal to customer then Card configuration options will be enables automticaly. so as to avoide feture issues. (PIN, Activation date & start date) 6. Image upload , Signature upload 7. Check / Make functionality 8. Scan documents to be uploaded if required ie PAN, Adhar, Pasport.
|  | Employee Left | 1. In this case employee will get deactivated. 2. Also delete status flag will be sent to reader/communication service. (Will check if the user's in time is availabe then after out time delete will trigger)
Temperory card
Employee Hierarchy
| Information Security compliance | 1. Password in web configuration will be stored in encrypted format 2. User's password will be stored in encrypted format. 3.
Pending Item list
| Leave Year End processsing |  | Service will be developed to handle this
Goles setting and Apprisal Review
Confirmation and evaluation
| date handling in Database and front end |  | dd/MMM/yyyy

## TimeLine
Sr No | Module | Pages | Priority | Development days | Testing | Code review | Re testing | Resource Name | Start Date | End date | Complexcity | Dependancy | Remark | Task Order | Status
1 | Database Compartablity base freamwork (Data Access layer) | NA | 1 | 20 | 5 | 3 | 3 | Sachin | 2018-06-26 | 2018-07-14 |  |  | This activity will go along with project development
2 | Core - admin confiuration | Menu master | 1 | 3 | 1 | 0.25 | 0.25 | Sachin | 2018-07-13 | 2018-07-17 |  |  |  |  | done
3 | Core - admin confiuration | Role / Level | 1 | 2 | 0.5 | 0.5 | 0.25 | Sachin | 2018-07-19 | 2018-07-20 |  |  |  |  | pending
4 | Core - admin confiuration | Role menu Configuration | 1 | 3 | 1 | 0.5 | 0.5 | Sachin | 2018-07-23 | 2018-07-25 |  |  |  |  | pending, company select bind role, role access
5 | Core - admin confiuration | User master | 1 | 2 | 1 | 0.5 | 0.5 | Yogesh | 2018-07-23 | 2018-07-24 |  |  |  | 2 | done
6 | Core - admin confiuration | Menu tree / Menu drop-down | 1 | 4 | 1 | 1 | 1 | Sachin | 2018-08-06 | 2018-08-09 |  |  |  |  | done, correction pending
7 | Core | Company | 1 | 2 | 1 | 0.5 | 1 | Yogesh | 2018-07-19 | 2018-07-20 |  |  |  | 1 | done
8 | Core | Common master | 1 | 2 | 1 | 0.5 | 0.5 | Yogesh | 2018-07-27 | 2018-07-30 |  |  |  | 3 | done
9 | Core | Holiday | 1 | 2 | 1.5 | 1 | 0.5 | Rajneesh | 2018-07-20 | 2018-07-23 |  |  |  | 3 | done, swap function pending
10 | Core | Reason | 1 | 2 | 0.5 | 0.5 | 0.5 | Yogesh | 2018-07-25 | 2018-07-26 |  |  |  | 4 | done
11 | Core | Employee | 1 | 3 | 1 | 1 | 0.5 | Rajneesh | 2018-07-24 | 2018-07-26 |  |  |  | 4 | done
12 | Core | Employee Hirerchy | 1 | 3 | 1 | 1 | 0.5 | Rajneesh | 2018-07-27 | 2018-07-31 |  |  |  | 5 | done
13 | Core | Employee Left | 1 | 2 | 0.5 | 0.5 | 0.5 | yogesh | 2018-07-31 | 2018-08-01 |  |  |  | 5 | done
14 | Core | Operational access / Data binding to login | 1 | 3 | 1 | 1 | 1 | Rajneesh | 2018-08-01 | 2018-08-03 |  |  |  | 6 | done
15 | Core - admin confiuration | Auto Backup Scheduler | 5 | 5 | 1 | 1 | 1 | [5 empty] | This feature will be there but has least priority
16 | Report | R& D | 1 | 5 |  |  |  | Sachin | 2018-07-30 | 2018-08-04 |  |  | Time requires will depends on feasible solution
17 | Sentinal -Core | Controller | 1 | 5 | 1 | 1 | 1 | Rajneesh | 2018-07-12 | 2018-07-17 |  |  |  | 1 | done
18 | Sentinal -Core | Zone | 1 | 2 | 1 | 1 | 1 | Rajneesh | 2018-07-18 | 2018-07-19 |  |  |  | 2 | done
19 | Sentinal -Core | Access Level | 1 | 4 | 1 | 1 | 1 | Rajneesh | 2018-08-04 | 2018-08-08 |  |  |  | 7 | done
20 | Sentinal -Core | Employee card configuration | 1 | 2 | 1 | 1 | 1 | Rajneesh | 2018-08-09 | 2018-08-10 |  |  | Need functional details for same. | 8 | done
21 | Sentinal -Core | Employee access configuration | 1 | 3 | 1 | 1 | 1 | Rajneesh | 2018-08-11 | 2018-08-13 |  |  | Need functional details for same. | 9 | done
22 | Sentinal -Core | time zone | 1 | 3 | 1 | 1 | 1 | Rajneesh | 2018-08-14 | 2018-08-17 |  |  | 15-Aug is holiday | 10 | pending
23 | Sentinal -Core | Building access | 2 | 3 | 1 | 1 | 1 | Rajneesh | 2018-08-13 | 2018-08-16 |  |  | Need functional details for same.
24 | Sentinal -Core | Reader message templete | 1 | 2 | 0.5 | 0.5 | 0.5 | Yogesh | 2018-08-02 | 2018-08-03 |  |  |  | 6 | done
25 | Sentinal -Core | ACS_Event_upload | 2 | 4 | 1 | 1 | 1 | Rajneesh | [6 empty] | pending
26 | Sentinal -Core | Finger Template Configuration | 1 | 3 | 1 | 1 | 0 | Yogesh | 2018-08-04 | 2018-08-07 |  |  |  | 7 | pending
27 | sentinal-Transaction | Activity Browser | 1 | 2 | 1 | 0.5 | 0.5 | Rajneesh | 2018-08-20 | 2018-08-21 |  |  |  | 11 | done, correction pending
28 | sentinal-Transaction | Event Viewer | 1 | 2 | 0.5 | 0.5 | 0.5 | Rajneesh | 2018-08-22 | 2018-08-23 |  |  |  | 12 | done, correction pending
29 | sentinal-Transaction | Update network | 2 |  |  |  |  | Rajneesh
30 | sentinal-Transaction | update template | 2 |  |  |  |  | Rajneesh
31 | sentinal-Transaction | Controller status | 1 | 2 | 0.5 | 0.5 | 0.5 | Yogesh | 2018-08-08 | 2018-08-09 |  |  |  | 8 | done, correction pending
32 | sentinal-Transaction | autocard lookup | 1 | 1 | 0.5 | 0.5 | 0.5 | Rajneesh | 2018-08-24 | 2018-08-24 |  |  |  | 13 | done, correction pending
33 | sentinal-Transaction | Locate card holder | 1 | 1 | 0.5 | 0.5 | 0.5 | Rajneesh | 2018-08-25 | 2018-08-25 |  |  |  | 14 | done, correction pending
34 | sentinal-Reports | Card holder details | 3 |  |  |  |  | Rajneesh
35 | sentinal-Reports | Controller master | 3 |  |  |  |  | Rajneesh
36 | sentinal-Reports | Access controll details | 3 |  |  |  |  | Rajneesh
37 | sentinal-Reports | alarm condition details | 3 |  |  |  |  | Rajneesh
38 | sentinal-Reports | access level | 3 |  |  |  |  | Rajneesh
39 | Visitor | Visitor request master | 1 | 5 | 1 | 0.5 | 0.5 | Aniket More | 2018-07-12 | 2018-07-18 |  |  |  |  | done
40 | Visitor | Visitor request approval | 1 | 3 | 1 | 0.5 | 0.5 | Aniket More | 2018-07-19 | 2018-07-23 |  |  |  |  | done
41 | Visitor | Gate pass | 2 | 4 | 1 | 0.5 | 0.5 | Yogesh | [5 empty] | 9
42 | Visitor | Visitor blacklist | 1 | 3 | 1 | 0.5 | 0.5 | Aniket More | [6 empty] | done
43 | Visitor | Visitor card reinitialise | 2 |  |  | 0.5 | 0.5 | Yogesh
44 | Visitor-Reports | Visitor list | 2 | 3 | 1 | 0.5 | 0.5 | Aniket More
45 | Visitor-Reports | Number of Visitors | 2 | 3 | 1 | 0.5 | 0.5 | Aniket More
46 | Visitor-Reports | Denial Visitors | 2 | 3 | 1 | 0.5 | 0.5 | Aniket More
47 | Visitor-Reports | OverStayed Visitors | 2 | 3 | 1 | 0.5 | 0.5 | Aniket More
48 | Visitor-Reports | Access / Movement for main Gate | 1 | 4 | 1 | 0.5 | 0.5 | Aniket More
49 | Visitor-Reports | Visitor Current strength | 1 | 3 | 1 | 0.5 | 0.5 | Aniket More
50